## README
Enterprise Risk Management Toolkit v4.1.1 - Demonstration
Connected workbook: methodology > appetite > risk register > breach monitor > treatment tracker > dashboard
PURPOSE
A connected ERM workbook covering all twelve Enterprise Risk Management resources in the GRC library, plus snapshot history and an audit trail. An analyst can use it through a real engagement: define the scoring method, set approved appetite and tolerance, score risks, detect breaches, escalate, record acceptances, monitor indicators and emerging risks, quantify scenarios, find concentrations, keep history and report. Everything is formula-driven and works offline.
HOW THE SHEETS CONNECT
FOUNDATION (P1): Methodology (scales, bands, control reductions, escalation, as-of date) > Appetite (threshold and tolerance per category) > Risk Register (scores inherent and residual risk, sets breach and governance status) > Breach Monitor (auto-lists breaches and required escalation) > Treatment Tracker (actions, overdue flags) > Dashboard.
P2: Risk Acceptance Register (formal decisions; feeds the Register's governance status and checks approver authority), KRI Tracker (leading indicators with RAG, trend and early warning), Risk-Control Matrix with RCM Summary (links risks to controls and tests the control effectiveness assumed in the Register), Emerging Risk Register (horizon scanning with velocity-weighted priority).
P3: Scenario Analysis (indicative loss scenarios with documented basis and confidence) and Risk Aggregation with Aggregation Map (concentration screening).
HISTORY: Snapshot Capture (live view with control totals) > Snapshot History (pasted values) > Snapshot Trends (trends, reconciliation, like-for-like movement vs changes in register composition). Change Log is a VOLUNTARY record, not a tamper-resistant audit trail. Exception Register holds the authorised exceptions that may offset integrity-check issues.
KEY DEFINITIONS
Appetite breach: residual score is above the category's appetite threshold. Tolerance breach: residual score is above the category's tolerance limit (a harder ceiling).
Formal acceptance is recorded only on the Risk Acceptance Register. Accepting a risk NEVER removes the breach: Breach Status stays as calculated, and Governance Status shows 'Breach - formally accepted'. If the acceptance expires or has no expiry date, the breach reappears as open. Acceptances are checked against the authority level required for the breach.
Residual risk: the authoritative residual score comes ONLY from an evidence-supported assessment (assessed likelihood and impact, evidence reference, assessor, approver and date within the validity period). Without one, the risk is scored on its inherent values: a control-effectiveness label alone earns no reduction. The control-reduction formula is kept as an indicative reference score only.
LIMITATIONS (READ BEFORE USE)
Risk scores are ordinal (1-25). They rank risks; they are not measurements and must not be added up as money. Scenario Analysis figures (frequency, loss ranges, treatment reductions) are analyst judgements with stated uncertainty, are indicative screening estimates, and are NOT financial forecasts. Risk Aggregation totals are a concentration screening index: a risk linked to several drivers counts in each, and no correlation or portfolio-loss modelling is done.
Snapshots are taken manually (Paste Special > Values) using the strict procedure on Snapshot Capture, and each must be reconciled against three control totals. Even so, there is no macro and no automatic timestamp, so history and the Change Log are only as trustworthy as the discipline of never editing past rows. They are voluntary records, not tamper-resistant: for assurance use file version control, protected sheets and access controls outside this workbook.
DATA QUALITY AND SETUP
This demonstration contains fictional records and intentional data-quality examples, including an expired assessment and a missing residual assessment. Checks reports these as sample data-quality issues. Exact scoped authority exceptions offset their matching check only and never grant acceptance authority. For your own records, start with the separate Clean Template workbook.
COLOUR LEGEND
Blue text on cream fill = cells you edit. Black on grey = formulas, do not overwrite. Navy = headers.
GETTING STARTED
Explore the fictional records to understand the workflow. Review Methodology, Appetite, Risk Register and the linked monitoring sheets. The demonstration status is a description of sample data, not release certification. Use the separate Clean Template to enter organisational data. Dashboard totals always include filtered-out records.
ASSUMPTIONS
All scales, bands (Low 1-4, Medium 5-9, High 10-16, Critical 17-25), control reductions (Strong 50%, Adequate 30%, Weak 10%, None 0%), velocity multipliers, appetite thresholds, escalation timeframes, loss tolerances, concentration thresholds and the 30-day snapshot frequency are illustrative defaults, not a mandated standard. Align them to your own risk policy. Sample data is fictional.
Capacity: 100 risks, 100 acceptances, 100 treatment actions, 60 KRIs, 150 risk-control mappings, 60 emerging risks, 50 scenarios, 20 drivers, 200 aggregation links, 1,000 snapshot rows, 500 change-log entries, 12 categories. Heatmap colours use the default bands. The as-of date defaults to TODAY(); overwrite Methodology!B4 with a fixed date to reproduce a past report.
Version 4.1.1. Desktop Excel recalculation tested; Excel for web unverified. The status reports setup and data-quality conditions, not production certification. Risk breaches remain visible even when accepted. Formula cells are unprotected; use controlled file access and preserve calculated columns. Fixed worksheet capacities apply.

## Dashboard
Enterprise Risk Dashboard
As of 23 Oct 2026 ¦ DEMONSTRATION: fictional data - 2 sample data-quality issue(s)
Headline metrics |  |  |  | Residual heatmap (number of risks)
Total risks on register | 8 |  |  | Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
Average inherent score | 12.875 |  |  | 5 | 0 | 0 | 1 | 0 | 0
Average residual score | 11.375 |  |  | 4 | 0 | 0 | 0 | 1 | 0
Residual High or Critical risks | 4 |  |  | 3 | 0 | 0 | 3 | 0 | 1
Risks in breach of appetite (all) | 5 |  |  | 2 | 0 | 0 | 0 | 1 | 1
of which tolerance breaches | 2 |  |  | 1 | 0 | 0 | 0 | 0 | 0
Breaches not accepted | 2 |  |  | Colours follow the default rating bands.
Breaches formally accepted | 1
Acceptances expired (breach reopened) | 1 |  |  | Rating distribution
Acceptances with no expiry date | 1 |  |  | Rating | Inherent | Residual
Breaches with no action and no valid acceptance | 1 |  |  | Low | 0 | 0
Open treatment actions | 4 |  |  | Medium | 2 | 4
Overdue treatment actions | 1 |  |  | High | 5 | 4
Actions due soon | 1 |  |  | Critical | 1 | 0
Risk reviews overdue | 1
Residual risks above target score | 8
Acceptances expiring soon | 0
Acceptances with insufficient approval authority | 1
KRIs in red | 3
Emerging risks flagged for escalation | 2
Indicative total ALE (GBP, not a forecast) | 478000
Concentration-flagged drivers (screening index) | 2
Days since last snapshot | 23
Risks scored on inherent basis (no valid residual assessment) | 2
Risk by category
Category | Risks | Avg residual score | Appetite threshold | Appetite breaches | Tolerance breaches
Strategic | 1 | 10 | 12 | 0 | 0
Operational | 0 | 0 | 9 | 0 | 0
Cyber & Information Security | 1 | 15 | 6 | 0 | 1
Compliance & Regulatory | 1 | 8 | 4 | 1 | 0
Financial | 1 | 9 | 9 | 0 | 0
Third-Party | 1 | 16 | 9 | 0 | 1
Technology | 1 | 15 | 9 | 1 | 0
Data Privacy | 1 | 9 | 6 | 1 | 0
People | 1 | 9 | 9 | 0 | 0

## Methodology
Risk Assessment Methodology
Scales, bands, control effectiveness and escalation rules. Blue cells are editable.
Residual assessment validity (days) | 365 | An evidence-supported residual assessment older than this is treated as expired.
As-of date | 2026-10-23 | Defaults to today. Overwrite with a fixed date to reproduce a past report.
Due-soon window (days) | 30 | Actions due within this many days are flagged 'Due soon'.
Max acceptance period (days) | 365 | Acceptances longer than this are flagged on the Risk Acceptance Register.
Snapshot frequency (days) | 30 | Dashboard flags when the latest snapshot is older than this.
Likelihood scale
Score | Level | Descriptor | Indicative frequency
1 | Rare | Would occur only in exceptional circumstances | Less than once in 10 years
2 | Unlikely | Could occur but not expected | Once in 5-10 years
3 | Possible | Might occur at some point | Once in 2-5 years
4 | Likely | Will probably occur | About once a year
5 | Almost certain | Expected to occur, possibly repeatedly | Several times a year
Impact scale
Score | Level | Financial | Operational | Regulatory / legal | Reputational
1 | Negligible | Under 1% of annual budget | Disruption under 1 hour | No regulatory interest | No external awareness
2 | Minor | 1-2% of annual budget | Disruption up to 1 working day | Minor internal breach, no reporting | Limited local awareness
3 | Moderate | 2-5% of annual budget | Disruption of 1-3 days | Reportable breach, informal regulator contact | Adverse local or sector media
4 | Major | 5-10% of annual budget | Disruption of 3-7 days | Formal investigation or enforcement notice | National adverse coverage, customer loss
5 | Severe | Over 10% of annual budget | Disruption over 7 days or loss of critical service | Fine, licence loss or prosecution | Sustained loss of public trust
Rating bands (score = likelihood x impact)
Min score | Rating | Max score | Required response
1 | Low | 4 | Accept and monitor through routine review
5 | Medium | 9 | Manage within business-as-usual controls; owner review quarterly
10 | High | 16 | Treatment plan required; senior management oversight
17 | Critical | 25 | Immediate action; executive attention and escalation
Score matrix
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5
Control effectiveness: INDICATIVE reference only (does not set authoritative residual risk)
Level | Likelihood reduction | Description
Strong | 50% | Controls designed and operating effectively, tested with evidence
Adequate | 30% | Controls in place and mostly effective, minor gaps
Weak | 10% | Controls exist but are poorly designed or inconsistently operated
None | 0% | No effective controls
Escalation rules
Breach status | Escalate to | Respond within (days) | Governance expectation
Within appetite | No escalation | 0 | Monitor through routine review
Appetite breach | Head of Risk / CISO | 30 | Treatment plan or formal acceptance with expiry
Tolerance breach | Executive Committee / Board | 7 | Immediate treatment; acceptance only at executive level
Emerging risk velocity multipliers
Velocity | Multiplier | Meaning
Slow | 0.8 | Years to materialise; time to respond
Moderate | 1 | Months to materialise
Fast | 1.2 | Weeks to materialise
Immediate | 1.4 | Little or no warning
Authoritative residual risk: requirements
A residual score is authoritative only when the Register holds assessed residual likelihood and impact PLUS an evidence reference, an assessor, an approver and an assessment date within the validity period above.
Otherwise the risk is scored on its INHERENT likelihood and impact: a control-effectiveness label alone earns no score reduction.
The calculated indicative residual (control reduction table above) is shown for reference only, so analysts can compare their evidence-based judgement against a simple formula.
Evidence examples: control test results, audit reports, incident and KRI data, supplier assurance outcomes. Record where the evidence is held, not the evidence itself.

## Appetite
Risk Appetite & Tolerance Matrix
Appetite threshold = maximum acceptable residual score. Tolerance limit = hard ceiling. Scores are on the Methodology 1-25 scale.
Risk category | Appetite level | Appetite threshold (score) | Tolerance limit (score) | Appetite statement | Approved by | Approval date | Next review | Validity check | Threshold version | Effective from
Strategic | Open | 12 | 20 | Willing to take risk in pursuit of strategic growth, within tolerance. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Operational | Cautious | 9 | 15 | Prefers resilient operations; accepts limited disruption risk. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Cyber & Information Security | Minimal | 6 | 10 | Low tolerance for threats to confidentiality, integrity or availability. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Compliance & Regulatory | Averse | 4 | 8 | Very low tolerance for regulatory or legal non-compliance. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Financial | Cautious | 9 | 15 | Accepts modest financial volatility with active monitoring. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Third-Party | Cautious | 9 | 15 | Accepts supplier risk where assurance and exit plans exist. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Technology | Cautious | 9 | 15 | Accepts limited technical-debt risk with funded remediation. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Data Privacy | Minimal | 6 | 10 | Low tolerance for unauthorised use or exposure of personal data. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
People | Cautious | 9 | 15 | Accepts limited workforce and key-person risk with succession plans. | Risk Committee | 2026-07-01 | 2027-07-01 | OK | v1.0 | 2026-07-01
Assumption: thresholds above are illustrative. Replace with limits approved by your board or risk committee. Provide up to 12 categories; the Register category dropdown reads this list.

## Risk Register
Cyber & Enterprise Risk Register
Blue = inputs. Residual risk is AUTHORITATIVE only with an evidence-supported assessment (cols K-L plus AE-AH); otherwise inherent scores apply. Rows 6-13 are SAMPLE.
RISK IDENTIFICATION |  |  |  |  | INHERENT RISK |  |  |  | CONTROLS & RESIDUAL RISK | [6 empty] | TARGET |  | APPETITE TEST |  |  | ACCEPTANCE & GOVERNANCE |  |  |  | REVIEW |  | HELPERS (do not edit) |  |  | RESIDUAL ASSESSMENT EVIDENCE (required for an authoritative residual)
Risk ID | Risk title | Description (cause > event > consequence) | Category | Risk owner | Inherent likelihood (1-5) | Inherent impact (1-5) | Inherent score | Inherent rating | Control effectiveness (indicative only) | Assessed residual likelihood (evidence-based) | Assessed residual impact (evidence-based) | Residual likelihood used | Residual impact used | Residual score (authoritative) | Residual rating | Target score | Gap to target | Appetite threshold | Tolerance limit | Breach status | Formally accepted? (auto) | Accepted by (auto) | Acceptance expiry (auto) | Governance status | Next review date | Review status | Breach seq | Open actions | Treatment gap | Evidence reference | Assessed by | Assessment date | Assessment approved by | Assessment status | Indicative residual score (calculated, reference only) | Residual basis | Approval decision (manual)
R-001 | Ransomware on production | Phishing leads to credential theft, ransomware spreads and encrypts tier-1 systems, halting trading. | Cyber & Information Security | CISO | 4 | 5 | 20 | Critical | Adequate | 3 | 5 | 3 | 5 | 15 | High | 8 | 7 | 6 | 10 | Tolerance breach | No |  |  | Breach - not accepted | 2026-11-30 | On schedule | 1 | 2 |  | EV-001 control test report CT-2026-14 | Security Analyst | 2026-09-15 | CISO | Valid | 15 | Assessed (evidence-supported) | Approved
R-002 | SaaS provider data breach | Weak supplier security leads to breach at the payroll SaaS provider, exposing employee data. | Third-Party | Head of Procurement | 4 | 4 | 16 | High | Weak | 4 | 4 | 4 | 4 | 16 | High | 9 | 7 | 9 | 15 | Tolerance breach | Yes | CFO | 2026-09-30 | Acceptance expired - breach open | 2026-09-15 | Overdue | 2 | 0 | Gap | EV-002 supplier assurance review 2026-Q3 | Procurement Analyst | 2026-09-20 | Head of Procurement | Valid | 16 | Assessed (evidence-supported) | Approved
R-003 | Sensitive data pasted into AI tools | Staff use unapproved AI services, leaking customer data outside approved boundaries. | Data Privacy | DPO | 3 | 3 | 9 | Medium | Weak | 3 | 3 | 3 | 3 | 9 | Medium | 4 | 5 | 6 | 10 | Appetite breach | Yes | Risk Committee | 2027-03-31 | Breach - formally accepted | 2026-12-15 | On schedule | 3 | 0 |  | EV-003 DLP pilot results | DPO | 2026-09-25 | Risk Committee | Valid | 9 | Assessed (evidence-supported) | Approved
R-004 | Missed regulatory deadlines | Manual tracking leads to late regulatory submissions and supervisory action. | Compliance & Regulatory | Head of Compliance | 3 | 4 | 12 | High | Strong | 2 | 4 | 2 | 4 | 8 | Medium | 4 | 4 | 4 | 8 | Appetite breach | No |  |  | Breach - not accepted | 2026-11-20 | On schedule | 4 | 1 |  | EV-004 compliance calendar test 2026-08 | Compliance Analyst | 2026-08-10 | Head of Compliance | Valid | 8 | Assessed (evidence-supported) | Approved
R-005 | Key-person dependency | Two engineers hold sole knowledge of the platform; departure disrupts delivery. | People | CTO | 4 | 3 | 12 | High | Adequate | 3 | 3 | 3 | 3 | 9 | Medium | 6 | 3 | 9 | 15 | Within appetite | No |  |  | Within appetite | 2027-01-31 | On schedule |  | 0 |  | EV-005 succession plan review | HR Business Partner | 2026-09-01 | CTO | Valid | 9 | Assessed (evidence-supported) | Approved
R-006 | Legacy ERP out of support | Vendor ends support; unpatched flaws and failures disrupt finance operations. | Technology | CIO | 5 | 3 | 15 | High | None | 5 | 3 | 5 | 3 | 15 | High | 6 | 9 | 9 | 15 | Appetite breach | Yes | CIO |  | Accepted - expiry not set | 2026-12-01 | On schedule | 5 | 1 |  | EV-006 vendor end-of-support notice | IT Architect | 2026-06-01 | CIO | Valid | 15 | Assessed (evidence-supported) | Approved
R-007 | Supplier price inflation | Input cost rises erode margin faster than pricing can adjust. | Financial | CFO | 3 | 3 | 9 | Medium | Adequate | 2 | 3 | 3 | 3 | 9 | Medium | 4 | 5 | 9 | 15 | Within appetite | No |  |  | Within appetite | 2027-02-28 | On schedule |  | 0 |  | EV-007 pricing review 2025 | Finance Analyst | 2025-09-15 | CFO | Expired | 6 | Inherent only (no valid assessment) | Approved
R-008 | Loss of anchor customer | Largest customer does not renew, removing 18% of revenue. | Strategic | CEO | 2 | 5 | 10 | High | Adequate |  |  | 2 | 5 | 10 | High | 5 | 5 | 12 | 20 | Within appetite | No |  |  | Within appetite | 2027-01-15 | On schedule |  | 0 | [5 empty] | No assessment | 5 | Inherent only (no valid assessment) | Approved

## Breach Monitor
Risk Appetite Breach Monitor
Automatically lists every risk whose residual score exceeds appetite. Acceptance never hides a breach: it changes the governance status only. No data entry here.
|  | Total breaches | Tolerance breaches | Not accepted | Formally accepted | Acceptance expired | Expiry not set | Treatment gaps
|  | 5 | 2 | 2 | 1 | 1 | 1 | 1
# | Register row | Risk ID | Risk title | Category | Risk owner | Residual score | Appetite threshold | Tolerance limit | Excess over appetite | Breach status | Governance status | Escalate to | Acceptance expiry | Days to expiry | Open actions | Required next action
1 | 1 | R-001 | Ransomware on production | Cyber & Information Security | CISO | 15 | 6 | 10 | 9 | Tolerance breach | Breach - not accepted | Executive Committee / Board |  |  | 2 | Escalate to Executive Committee / Board; track treatment actions
2 | 2 | R-002 | SaaS provider data breach | Third-Party | Head of Procurement | 16 | 9 | 15 | 7 | Tolerance breach | Acceptance expired - breach open | Executive Committee / Board | 2026-09-30 | -23 | 0 | Acceptance lapsed: re-approve or treat
3 | 3 | R-003 | Sensitive data pasted into AI tools | Data Privacy | DPO | 9 | 6 | 10 | 3 | Appetite breach | Breach - formally accepted | Head of Risk / CISO | 2027-03-31 | 159 | 0 | Accepted: monitor to expiry and keep treating where practical
4 | 4 | R-004 | Missed regulatory deadlines | Compliance & Regulatory | Head of Compliance | 8 | 4 | 8 | 4 | Appetite breach | Breach - not accepted | Head of Risk / CISO |  |  | 1 | Escalate to Head of Risk / CISO; track treatment actions
5 | 6 | R-006 | Legacy ERP out of support | Technology | CIO | 15 | 9 | 15 | 6 | Appetite breach | Accepted - expiry not set | Head of Risk / CISO |  |  | 1 | Set an acceptance expiry date
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Formulas:
Acceptance expiry = IF([Register row]="","",IF(INDEX('Risk Register'!$X6:X105,[Register row])="","",INDEX('Risk Register'!$X6:X105,[Register row])))

## Treatment Tracker
Risk Treatment Tracker
One row per mitigation action, linked to a Risk ID. Capacity: 100 actions. Rows 6-10 are SAMPLE data.
Action ID | Risk ID | Risk title | Action description | Action owner | Start date | Due date | Status | % complete | Completion date | Days overdue | Action flag | Expected residual score after action | Residual score now | Expected reduction | Notes
A-001 | R-001 | Ransomware on production | Deploy immutable offline backups for tier-1 systems | IT Operations | 2026-08-01 | 2026-11-30 | In progress | 40% |  | 0 | On track | 8 | 15 | 7 | Quarterly restore test planned
A-002 | R-001 | Ransomware on production | Extend EDR to remaining endpoints | IT Operations | 2026-07-01 | 2026-09-30 | In progress | 70% |  | 23 | Overdue | 10 | 15 | 5 | Delayed by device procurement
A-003 | R-004 | Missed regulatory deadlines | Automate regulatory calendar with escalation alerts | Head of Compliance | 2026-10-15 | 2026-11-15 | Not started | 0% |  | 0 | Due soon | 4 | 8 | 4
A-004 | R-006 | Legacy ERP out of support | Approve business case for ERP replacement | CIO | 2026-09-01 | 2027-02-28 | In progress | 25% |  | 0 | On track | 6 | 15 | 9
A-005 | R-005 | Key-person dependency | Cross-train two engineers on platform operations | CTO | 2026-06-01 | 2026-08-30 | Completed | 100% | 2026-08-28 |  | Complete | 6 | 9 | 3

## Risk Acceptance Register
Risk Acceptance Register
Formal decisions to accept a risk above appetite. Accepting never removes the breach: the Risk Register keeps the breach status and shows the governance status. Rows 6-9 are SAMPLE data.
An eligible acceptance requires an approved decision, named approver, rationale, valid current dates, permitted duration and sufficient authority. Exceptions offset a check only; they do not grant authority. The last eligible worksheet record supplies displayed approver and expiry. Review duplicate decisions and sort by decision date if chronological precedence is needed.
Acceptance ID | Risk ID | Risk title | Category | Current residual score | Current breach status | Rationale for acceptance | Conditions / compensating measures | Decision | Approver name | Approver authority level | Decision date | Expiry date | Authority required | Authority check | Acceptance status | Days to expiry | Flags | Matched approved exception (auto) | Acceptance eligibility (auto)
AC-001 | R-002 | SaaS provider data breach | Third-Party | 16 | Tolerance breach | Supplier migration planned; interim monitoring in place. | Quarterly assurance review; exit plan drafted. | Approved | CFO | Head of Risk / CISO | 2026-04-01 | 2026-09-30 | Executive Committee / Board | Insufficient authority | Expired | -23 |  | 1 | Expired
AC-002 | R-003 | Sensitive data pasted into AI tools | Data Privacy | 9 | Appetite breach | Business needs AI productivity tools while DLP is deployed. | Approved tools list only; DLP rollout by Q1. | Approved | Risk Committee | Head of Risk / CISO | 2026-09-30 | 2027-03-31 | Head of Risk / CISO | OK | Active | 159 |  | 0 | Eligible
AC-003 | R-006 | Legacy ERP out of support | Technology | 15 | Appetite breach | Replacement funded in next financial year budget. | Extended vendor support contract in place. | Approved | CIO | Head of Risk / CISO | 2026-06-01 |  | Head of Risk / CISO | OK | Approved - no expiry |  |  | 0 | Decision or expiry date missing/invalid
AC-004 | R-004 | Missed regulatory deadlines | Compliance & Regulatory | 8 | Appetite breach | Awaiting delivery of regulatory calendar automation. | Manual weekly check by compliance team. | Pending | Head of Compliance |  |  |  | Head of Risk / CISO |  | Pending |  |  | 0 | Not approved
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## KRI Tracker
Key Risk Indicator Tracker
Track leading indicators against amber/red thresholds. Enter readings left to right with no gaps; when full, shift older readings out. Rows 6-11 are SAMPLE data.
For 'Lower is worse' indicators set the red threshold below the amber threshold (e.g. amber 98, red 95).
[11 empty] | Period labels (edit): | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26
KRI ID | Indicator | Linked Risk ID | Risk title | Category | Owner | Unit | Direction | Amber threshold | Red threshold | Update frequency (days) | Last updated | Reading 1 (oldest) | Reading 2 | Reading 3 | Reading 4 | Reading 5 | Reading 6 (latest) | Latest reading | Previous reading | RAG status | Trend | Update status | Linked risk status | Early-warning flag
K-001 | Phishing click rate | R-001 | Ransomware on production | Cyber & Information Security | Security Awareness Lead | % | Higher is worse | 5 | 10 | 30 | 2026-10-15 | 3 | 4 | 6 | 8 | 9 | 11 | 11 | 9 | Red | Worsening | Current | Tolerance breach
K-002 | Critical vulnerabilities open beyond SLA | R-001 | Ransomware on production | Cyber & Information Security | Vulnerability Manager | count | Higher is worse | 5 | 10 | 30 | 2026-08-31 | 3 | 4 | 4 | 5 | 6 | 6 | 6 | 6 | Amber | Stable | Overdue | Tolerance breach
K-003 | Suppliers with expired security assurance | R-002 | SaaS provider data breach | Third-Party | Head of Procurement | % | Higher is worse | 10 | 20 | 30 | 2026-10-15 | 8 | 12 | 14 | 18 | 22 | 24 | 24 | 22 | Red | Worsening | Current | Tolerance breach
K-004 | Regulatory submissions filed on time | R-004 | Missed regulatory deadlines | Compliance & Regulatory | Head of Compliance | % | Lower is worse | 98 | 95 | 30 | 2026-10-15 | 99 | 99 | 98 | 97 | 96 | 96 | 96 | 96 | Amber | Stable | Current | Appetite breach
K-005 | Voluntary turnover, platform team (annualised) | R-005 | Key-person dependency | People | CTO | % | Higher is worse | 10 | 15 | 30 | 2026-10-15 | 6 | 7 | 9 | 12 | 14 | 16 | 16 | 14 | Red | Worsening | Current | Within appetite | Early warning: KRI red while risk is within appetite
K-006 | Revenue share of largest customer | R-008 | Loss of anchor customer | Strategic | CFO | % | Higher is worse | 15 | 25 | 90 | 2026-10-01 |  | 17 | 17 | 18 | 18 | 18 | 18 | 18 | Amber | Stable | Current | Within appetite

## Risk-Control Matrix
Risk & Control Matrix
One row per risk-control pairing (a control can support several risks; a risk can have several controls). Rows 6-12 are SAMPLE data.
Mapping ID | Risk ID | Risk title | Residual score | Control ID | Control name | Control type | Control owner | Design assessment | Operating assessment | Last tested | Test frequency (days) | Next test due | Control rating | Test status | Notes
M-001 | R-001 | Ransomware on production | 15 | C-01 | Endpoint detection and response | Preventive | IT Operations | Effective | Partially effective | 2026-07-15 | 180 | 2027-01-11 | Partially effective | Current | 85% endpoint coverage
M-002 | R-001 | Ransomware on production | 15 | C-02 | Offline immutable backups | Corrective | IT Operations | Partially effective | Not tested |  | 180 |  | Not tested | No test date
M-003 | R-001 | Ransomware on production | 15 | C-03 | Email filtering and phishing training | Preventive | Security Awareness Lead | Effective | Effective | 2026-05-01 | 180 | 2026-10-28 | Effective | Current
M-004 | R-002 | SaaS provider data breach | 16 | C-10 | Supplier security assurance reviews | Detective | Head of Procurement | Partially effective | Ineffective | 2026-01-10 | 180 | 2026-07-09 | Ineffective | Overdue | Reviews not completed for 3 suppliers
M-005 | R-003 | Sensitive data pasted into AI tools | 9 | C-30 | AI acceptable-use policy | Preventive | DPO | Partially effective | Not tested |  | 365 |  | Not tested | No test date
M-006 | R-004 | Missed regulatory deadlines | 8 | C-20 | Regulatory submissions calendar | Detective | Head of Compliance | Effective | Partially effective | 2026-08-01 | 90 | 2026-10-30 | Partially effective | Current
M-007 | R-008 | Loss of anchor customer | 10 | C-40 | Executive account management reviews | Detective | CEO | Effective | Effective | 2026-09-01 | 365 | 2027-09-01 | Effective | Current
Formulas:
Next test due = IF(OR([Last tested]="",[Test frequency (days)]=""),"",[Last tested]+[Test frequency (days)])

## RCM Summary
Risk-Control Coverage Summary
Calculated from the Risk & Control Matrix. Compares the control effectiveness assumed in the Risk Register with what the control assessments support. No data entry.
Suggested effectiveness: None = no mapped controls; Strong = all Effective; Adequate = (Effective + 0.5 x Partially effective) / controls is 50% or more; otherwise Weak. Illustrative rule: edit the formulas in column J to suit your policy.
Risk ID | Risk title | Residual rating | Mapped controls | Effective | Partially effective | Ineffective | Not tested | Overdue tests | Suggested effectiveness | Register effectiveness | Alignment | Coverage flag
R-001 | Ransomware on production | High | 3 | 1 | 1 | 0 | 1 | 0 | Adequate | Adequate | Aligned
R-002 | SaaS provider data breach | High | 1 | 0 | 0 | 1 | 0 | 1 | Weak | Weak | Aligned | No fully effective control
R-003 | Sensitive data pasted into AI tools | Medium | 1 | 0 | 0 | 0 | 1 | 0 | Weak | Weak | Aligned | No fully effective control
R-004 | Missed regulatory deadlines | Medium | 1 | 0 | 1 | 0 | 0 | 0 | Adequate | Strong | Review: register says Strong | No fully effective control
R-005 | Key-person dependency | Medium | 0 | 0 | 0 | 0 | 0 | 0 | None | Adequate | Review: register says Adequate | No controls mapped
R-006 | Legacy ERP out of support | High | 0 | 0 | 0 | 0 | 0 | 0 | None | None | Aligned | No controls mapped
R-007 | Supplier price inflation | Medium | 0 | 0 | 0 | 0 | 0 | 0 | None | Adequate | Review: register says Adequate | No controls mapped
R-008 | Loss of anchor customer | High | 1 | 1 | 0 | 0 | 0 | 0 | Strong | Adequate | Review: register says Adequate

## Emerging Risks
Emerging Risk Register
Horizon-scanning log. Priority = impact x plausibility, weighted by velocity (Methodology sheet). High/Critical items are flagged for promotion to the Risk Register. Rows 6-10 are SAMPLE data.
ID | Emerging risk | Description | Source of signal | Category | Owner | Date identified | Time horizon | Velocity | Potential impact (1-5) | Plausibility (1-5) | Base score | Velocity multiplier | Priority score | Priority rating | Status | Early-warning trigger | Promoted to Risk ID | Next review | Review status | Recommendation
E-001 | Quantum-capable adversaries break current encryption | Cryptographic standards weaken faster than migration plans assume. | National cyber agency horizon scan | Cyber & Information Security | CISO | 2026-07-10 | 5+ years | Slow | 5 | 2 | 10 | 0.8 | 8 | Medium | Watching | Published standards deprecation dates |  | 2027-01-10 | On schedule
E-002 | Autonomous AI agents misuse delegated credentials | Agentic tools act on staff credentials beyond intended scope. | Vendor roadmap review | Cyber & Information Security | CISO | 2026-08-20 | 1-3 years | Fast | 4 | 4 | 16 | 1.2 | 19 | Critical | Assessing | First internal pilot of agent tooling |  | 2026-11-20 | On schedule | Consider escalating to Risk Register
E-003 | Operational resilience rules extended to critical suppliers | New regulation could impose direct obligations and audit rights on suppliers. | Regulator consultation paper | Compliance & Regulatory | Head of Compliance | 2026-09-05 | 1-3 years | Moderate | 3 | 4 | 12 | 1 | 12 | High | Watching | Final rules published |  | 2026-12-05 | On schedule | Consider escalating to Risk Register
E-004 | Regional energy supply disruption | Prolonged outages at the primary data centre region. | Supplier briefing | Operational | COO | 2026-06-15 | <1 year | Fast | 3 | 2 | 6 | 1.2 | 7 | Medium | Watching | Grid alert level raised |  | 2026-10-01 | Overdue
E-005 | Deepfake-enabled payment fraud | Synthetic voice or video used to authorise fraudulent transfers. | Industry fraud bulletin | Financial | CFO | 2026-09-25 | <1 year | Immediate | 4 | 4 | 16 | 1.4 | 22 | Critical | Escalated to register | Attempted fraud reported |  | 2026-12-25 | On schedule | Add Risk ID of promoted risk

## Scenario Analysis
Risk Scenario Analysis Workbook
SIMPLIFIED MODEL (PERT point estimates, independent scenarios, no distribution or correlation). Figures are indicative and uncertain, NOT financial forecasts. Rows 8-12 are SAMPLE. GBP.
INDICATIVE ONLY: document assumptions and confidence in V:Y. F:I and treatment cost must be numeric and nonnegative; loss bounds ordered; L:M must be between 0 and 100%. Invalid rows produce no loss estimate and block the portfolio tolerance status. Capacity: rows 8:57 only.
Annual loss tolerance (GBP) | 750000 |  | Indicative total ALE | Indicative treated ALE | Indicative ALE reduction | Portfolio ALE vs annual tolerance | Scenarios above single-event tolerance
Single-event loss tolerance (GBP) | 1500000 |  | 478000 | 223641.6667 | 254358.3333 | Within tolerance | 1
Scenario ID | Scenario | Risk ID | Category | Description | Annual frequency (events/yr) | Minimum loss | Most likely loss | Severe (maximum) loss | Expected loss per event | Indicative ALE (screening estimate) | Frequency reduction from treatment | Loss reduction from treatment | Indicative treated ALE | ALE reduction | Annual treatment cost | Net benefit | Benefit / cost ratio | Severe-loss test | Rank by ALE | Input check | Basis for frequency estimate | Basis for loss estimates | Basis for treatment reductions | Confidence in estimates | ALE low (frequency x minimum loss) | ALE high (frequency x severe loss) | Documentation check
S-001 | Ransomware halts production for 10 days | R-001 | Cyber & Information Security | Encryption of tier-1 systems after credential theft. | 0.15 | 150000 | 600000 | 3500000 | 1008333.3333 | 151250 | 40% | 30% | 63525 | 87725 | 120000 | -32275 | 0.73104 | Exceeds single-event tolerance | 1 | OK | Sector incident rates adjusted for our controls (analyst judgement) | Recovery cost, 10 days lost trading, legal; range from analyst workshop | Immutable backups assumed to cut recovery time; 30% loss reduction is an assumption | Low | 22500 | 525000 | Documented
S-002 | Payroll SaaS provider data breach | R-002 | Third-Party | Employee records exposed through supplier compromise. | 0.25 | 80000 | 250000 | 1200000 | 380000 | 95000 | 30% | 20% | 53200 | 41800 | 40000 | 1800 | 1.045 | Within tolerance | 3 | OK | One supplier breach in 4 years across 6 critical suppliers | Notification, credit monitoring, regulator contact | Assurance reviews assumed to reduce likelihood modestly | Medium | 20000 | 300000 | Documented
S-003 | Customer data leaked via AI tools | R-003 | Data Privacy | Staff paste personal data into unapproved services. | 0.5 | 20000 | 80000 | 400000 | 123333.3333 | 61666.6667 | 50% | 10% | 27750 | 33916.6667 | 15000 | 18916.6667 | 2.2611 | Within tolerance | 4 | OK | No recorded incidents; estimated from DLP alert volumes | Per-record breach cost x records plausibly exposed | DLP assumed to block half of leaks once deployed | Low | 10000 | 200000 | Documented
S-004 | Late regulatory submission penalty | R-004 | Compliance & Regulatory | Missed deadline triggers fine and remediation cost. | 0.3 | 25000 | 100000 | 750000 | 195833.3333 | 58750 | 60% | 0% | 23500 | 35250 | 30000 | 5250 | 1.175 | Within tolerance | 5 | OK | Two late submissions in past 3 years | Penalty schedule plus remediation staff time | Automated calendar assumed to remove most misses | High | 7500 | 225000 | Documented
S-005 | Legacy ERP outage during month-end | R-006 | Technology | Unsupported platform fails; manual workarounds required. | 0.4 | 50000 | 180000 | 900000 | 278333.3333 | 111333.3333 | 0% | 50% | 55666.6667 | 55666.6667 | 200000 | -144333.3333 | 0.27833 | Within tolerance | 2 | OK | Vendor failure bulletins and internal outage history | Manual workaround cost and month-end delay | Extended support assumed to shorten outages only | Medium | 20000 | 360000 | Documented
METHOD NOTES AND LIMITATIONS
1. Frequency, loss ranges and treatment reductions are analyst judgements, not measured data. Record the basis and your confidence for each scenario (columns V-Y).
2. Expected loss per event uses a three-point PERT weighting (minimum + 4 x most likely + severe) / 6. It does not model the full loss distribution.
3. ALE = frequency x expected loss. ALE low/high (frequency x minimum loss, frequency x severe loss) show a crude range, not a confidence interval.
4. Treatment reductions are assumed, not demonstrated: they presume the action is delivered and works as intended.
5. Scenarios are treated independently. No correlation, aggregation or tail modelling is done, so do not sum ALE as a forecast of annual loss.
6. Use for prioritisation and discussion only. Do not use as a financial forecast, provision or insurance limit.

## Risk Aggregation
Risk Aggregation Workbook
Concentration SCREENING: finds shared drivers (suppliers, systems, teams, processes) behind several risks. Link risks to drivers on the Aggregation Map sheet. Rows 10-13 are SAMPLE data.
SCREENING ONLY: driver totals add ordinal risk scores, which are not additive and not a measure of financial exposure. A risk linked to several drivers counts in each. True portfolio-loss aggregation (correlation, simulation) is out of scope.
Concentration: minimum linked risks | 3 |  |  | Indicative portfolio ALE (each scenario once) | Sum of driver-linked ALE (overlapping) | Overlap multiple (linked / portfolio) | Risks linked to 2+ drivers
Concentration: share of total residual score | 30% |  |  | 478000 | 740583.3333 | 1.5493 | 2
Total index, all risks (each risk once) | 91
Shares can total more than 100% because of overlapping links. Use the portfolio view (E4:H5) for a figure without double counting.
Exposure driver | Driver type | Linked risks | Concentration index (sum of residual scores) | Share of total index | Highest single residual | Linked breaches | Linked indicative ALE (GBP, overlaps) | Concentration indicator (screening) | Rank
Corporate network & identity platform | Asset / system | 3 | 39 | 42.86% | 15 | 3 | 324250 | High concentration | 1
Platform engineering team | People | 3 | 39 | 42.86% | 15 | 2 | 262583.3333 | High concentration | 1
Payroll SaaS provider | Supplier | 2 | 24 | 26.37% | 16 | 2 | 153750 |  | 3
Anchor customer relationship | Customer | 2 | 19 | 20.88% | 10 | 0 | 0 |  | 4

## Aggregation Map
Aggregation Map
Link each risk to the shared drivers behind it (one row per risk-driver pair). Drivers are defined on the Risk Aggregation sheet. Rows 6-15 are SAMPLE data.
Risk ID | Exposure driver | Risk title | Category | Residual score | In breach of appetite? | Indicative scenario ALE (GBP) | Duplicate check
R-001 | Corporate network & identity platform | Ransomware on production | Cyber & Information Security | 15 | Yes | 151250
R-003 | Corporate network & identity platform | Sensitive data pasted into AI tools | Data Privacy | 9 | Yes | 61666.6667
R-006 | Corporate network & identity platform | Legacy ERP out of support | Technology | 15 | Yes | 111333.3333
R-005 | Platform engineering team | Key-person dependency | People | 9 | No | 0
R-001 | Platform engineering team | Ransomware on production | Cyber & Information Security | 15 | Yes | 151250
R-006 | Platform engineering team | Legacy ERP out of support | Technology | 15 | Yes | 111333.3333
R-002 | Payroll SaaS provider | SaaS provider data breach | Third-Party | 16 | Yes | 95000
R-004 | Payroll SaaS provider | Missed regulatory deadlines | Compliance & Regulatory | 8 | Yes | 58750
R-008 | Anchor customer relationship | Loss of anchor customer | Strategic | 10 | No | 0
R-007 | Anchor customer relationship | Supplier price inflation | Financial | 9 | No | 0

## Snapshot Capture
Snapshot Capture
Live point-in-time view of the register. Freeze it into history with Paste Special > Values, then reconcile on Snapshot Trends. No macros, so it works offline.
Snapshot label | Q4 2026 review |  | Risks to copy | 8 | Copy rows 6 to | 13 |  | Control: sum of residual scores | 91 | Control: breaches | 5
STRICT PROCEDURE: 1) Set Methodology!B4 to a fixed reporting date (not TODAY()). 2) Confirm Checks shows no unresolved defects. 3) Enter the label. 4) Copy A6 to V(row in G3) only. 5) Paste Special > Values at the first empty row of Snapshot History, never over existing rows. 6) Record the three control totals (E3, J3, L3) on Snapshot Trends and confirm 'Reconciled'. 7) Log the capture in the Change Log.
Snapshot date | Snapshot label | Risk ID | Risk title | Category | Risk owner | Inherent score | Residual likelihood | Residual impact | Residual score | Residual rating | Appetite threshold | Tolerance limit | Breach status | Governance status | Control effectiveness (Register, indicative) | Control effectiveness (RCM suggested) | Open treatment actions | Treatment gap | Acceptance expiry | Appetite threshold version | Residual basis
2026-10-23 | Q4 2026 review | R-001 | Ransomware on production | Cyber & Information Security | CISO | 20 | 3 | 5 | 15 | High | 6 | 10 | Tolerance breach | Breach - not accepted | Adequate | Adequate | 2 |  |  | v1.0 | Assessed (evidence-supported)
2026-10-23 | Q4 2026 review | R-002 | SaaS provider data breach | Third-Party | Head of Procurement | 16 | 4 | 4 | 16 | High | 9 | 15 | Tolerance breach | Acceptance expired - breach open | Weak | Weak | 0 | Gap | 2026-09-30 | v1.0 | Assessed (evidence-supported)
2026-10-23 | Q4 2026 review | R-003 | Sensitive data pasted into AI tools | Data Privacy | DPO | 9 | 3 | 3 | 9 | Medium | 6 | 10 | Appetite breach | Breach - formally accepted | Weak | Weak | 0 |  | 2027-03-31 | v1.0 | Assessed (evidence-supported)
2026-10-23 | Q4 2026 review | R-004 | Missed regulatory deadlines | Compliance & Regulatory | Head of Compliance | 12 | 2 | 4 | 8 | Medium | 4 | 8 | Appetite breach | Breach - not accepted | Strong | Adequate | 1 |  |  | v1.0 | Assessed (evidence-supported)
2026-10-23 | Q4 2026 review | R-005 | Key-person dependency | People | CTO | 12 | 3 | 3 | 9 | Medium | 9 | 15 | Within appetite | Within appetite | Adequate | None | 0 |  |  | v1.0 | Assessed (evidence-supported)
2026-10-23 | Q4 2026 review | R-006 | Legacy ERP out of support | Technology | CIO | 15 | 5 | 3 | 15 | High | 9 | 15 | Appetite breach | Accepted - expiry not set | None | None | 1 |  |  | v1.0 | Assessed (evidence-supported)
2026-10-23 | Q4 2026 review | R-007 | Supplier price inflation | Financial | CFO | 9 | 3 | 3 | 9 | Medium | 9 | 15 | Within appetite | Within appetite | Adequate | None | 0 |  |  | v1.0 | Inherent only (no valid assessment)
2026-10-23 | Q4 2026 review | R-008 | Loss of anchor customer | Strategic | CEO | 10 | 2 | 5 | 10 | High | 12 | 20 | Within appetite | Within appetite | Adequate | Strong | 0 |  |  | v1.0 | Inherent only (no valid assessment)
Formulas:
Acceptance expiry = IF([Snapshot date]="","",'Risk Register'!X7)

## Snapshot History
Snapshot History (append-only by convention)
Pasted values only: one block of rows per snapshot. Never edit or delete past rows. Rows 6-21 are SAMPLE history (two fictional snapshots).
Snapshot date | Snapshot label | Risk ID | Risk title | Category | Risk owner | Inherent score | Residual likelihood | Residual impact | Residual score | Residual rating | Appetite threshold | Tolerance limit | Breach status | Governance status | Control effectiveness (Register, indicative) | Control effectiveness (RCM suggested) | Open treatment actions | Treatment gap | Acceptance expiry | Appetite threshold version | Residual basis | Lookup key (auto)
2026-08-31 | Aug 2026 review | R-001 | Ransomware on production | Cyber & Information Security | CISO | 20 | 4 | 5 | 20 | Critical | 6 | 10 | Tolerance breach | Breach - not accepted | Weak | Weak | 2 |  |  | v1.0 | Assessed (evidence-supported) | 46265¦R-001
2026-08-31 | Aug 2026 review | R-002 | SaaS provider data breach | Third-Party | Head of Procurement | 12 | 3 | 4 | 12 | High | 9 | 15 | Appetite breach | Breach - formally accepted | Weak | Weak | 0 |  | 2026-09-30 | v1.0 | Assessed (evidence-supported) | 46265¦R-002
2026-08-31 | Aug 2026 review | R-004 | Missed regulatory deadlines | Compliance & Regulatory | Head of Compliance | 12 | 3 | 4 | 12 | High | 4 | 8 | Tolerance breach | Breach - not accepted | Weak | Adequate | 0 | Gap |  | v1.0 | Assessed (evidence-supported) | 46265¦R-004
2026-08-31 | Aug 2026 review | R-005 | Key-person dependency | People | CTO | 12 | 3 | 3 | 9 | Medium | 9 | 15 | Within appetite | Within appetite | Adequate | None | 0 |  |  | v1.0 | Assessed (evidence-supported) | 46265¦R-005
2026-08-31 | Aug 2026 review | R-006 | Legacy ERP out of support | Technology | CIO | 15 | 5 | 3 | 15 | High | 9 | 15 | Appetite breach | Accepted - expiry not set | None | None | 0 | Gap |  | v1.0 | Assessed (evidence-supported) | 46265¦R-006
2026-08-31 | Aug 2026 review | R-007 | Supplier price inflation | Financial | CFO | 9 | 2 | 3 | 6 | Medium | 9 | 15 | Within appetite | Within appetite | Adequate | None | 0 |  |  | v1.0 | Assessed (evidence-supported) | 46265¦R-007
2026-08-31 | Aug 2026 review | R-008 | Loss of anchor customer | Strategic | CEO | 10 | 2 | 5 | 10 | High | 12 | 20 | Within appetite | Within appetite | Adequate | Strong | 0 |  |  | v1.0 | Inherent only (no valid assessment) | 46265¦R-008
2026-09-30 | Sep 2026 review | R-001 | Ransomware on production | Cyber & Information Security | CISO | 20 | 3 | 5 | 15 | High | 6 | 10 | Tolerance breach | Breach - not accepted | Adequate | Adequate | 2 |  |  | v1.0 | Assessed (evidence-supported) | 46295¦R-001
2026-09-30 | Sep 2026 review | R-002 | SaaS provider data breach | Third-Party | Head of Procurement | 16 | 4 | 4 | 16 | High | 9 | 15 | Tolerance breach | Breach - formally accepted | Weak | Weak | 0 |  | 2026-09-30 | v1.0 | Assessed (evidence-supported) | 46295¦R-002
2026-09-30 | Sep 2026 review | R-003 | Sensitive data pasted into AI tools | Data Privacy | DPO | 9 | 3 | 3 | 9 | Medium | 6 | 10 | Appetite breach | Breach - formally accepted | Weak | Weak | 0 |  | 2027-03-31 | v1.0 | Assessed (evidence-supported) | 46295¦R-003
2026-09-30 | Sep 2026 review | R-004 | Missed regulatory deadlines | Compliance & Regulatory | Head of Compliance | 12 | 2 | 4 | 8 | Medium | 4 | 8 | Appetite breach | Breach - not accepted | Strong | Adequate | 0 | Gap |  | v1.0 | Assessed (evidence-supported) | 46295¦R-004
2026-09-30 | Sep 2026 review | R-005 | Key-person dependency | People | CTO | 12 | 3 | 3 | 9 | Medium | 9 | 15 | Within appetite | Within appetite | Adequate | None | 0 |  |  | v1.0 | Assessed (evidence-supported) | 46295¦R-005
2026-09-30 | Sep 2026 review | R-006 | Legacy ERP out of support | Technology | CIO | 15 | 5 | 3 | 15 | High | 9 | 15 | Appetite breach | Accepted - expiry not set | None | None | 1 |  |  | v1.0 | Assessed (evidence-supported) | 46295¦R-006
2026-09-30 | Sep 2026 review | R-007 | Supplier price inflation | Financial | CFO | 9 | 3 | 3 | 9 | Medium | 9 | 15 | Within appetite | Within appetite | Adequate | None | 0 |  |  | v1.0 | Inherent only (no valid assessment) | 46295¦R-007
2026-09-30 | Sep 2026 review | R-008 | Loss of anchor customer | Strategic | CEO | 10 | 2 | 5 | 10 | High | 12 | 20 | Within appetite | Within appetite | Adequate | Strong | 0 |  |  | v1.0 | Inherent only (no valid assessment) | 46295¦R-008

## Snapshot Trends
Snapshot Trends, Reconciliation & Risk Movement
Calculated from Snapshot History. Enter each snapshot date and its three control totals (from Snapshot Capture). Pick two dates to compare. Distinguishes like-for-like movement from changes in register composition.
Current snapshot date | 2026-09-30 |  | Risks in both snapshots | New in current | Removed since comparison | Like-for-like risks (same threshold version and basis) | Like-for-like avg residual change | Like-for-like breach change | Total breach change (incl. composition)
Comparison snapshot date | 2026-08-31 |  | 7 | 1 | 0 | 6 | -0.83333 | 0 | 1
Register composition changed (1 new, 0 removed): judge movement on the like-for-like figures, not the totals.
Snapshot date | Label | Risks captured | Avg residual score | Residual High / Critical | Appetite breaches (all) | Tolerance breaches | Breaches not accepted | Formally accepted | Acceptance lapsed or no expiry | Treatment gaps | Weak / no control effectiveness | Change in breaches vs previous | Control total: risks (Capture E3) | Control total: sum of residual (Capture J3) | Control total: breaches (Capture L3) | Reconciliation
2026-08-31 | Aug 2026 review | 7 | 12 | 5 | 4 | 2 | 2 | 1 | 1 | 2 | 4 |  | 7 | 84 | 4 | Reconciled
2026-09-30 | Sep 2026 review | 8 | 11.375 | 4 | 5 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 8 | 91 | 5 | Reconciled
Risk movement between the comparison and current snapshots (risks on the live register)
Risk ID | Risk title | Prior residual | Current residual | Change | Prior breach status | Current breach status | Prior governance status | Current governance status | Movement | Prior appetite version | Current appetite version | Prior residual basis | Current residual basis | Comparability
R-001 | Ransomware on production | 20 | 15 | -5 | Tolerance breach | Tolerance breach | Breach - not accepted | Breach - not accepted | Improved | v1.0 | v1.0 | Assessed (evidence-supported) | Assessed (evidence-supported) | Like-for-like
R-002 | SaaS provider data breach | 12 | 16 | 4 | Appetite breach | Tolerance breach | Breach - formally accepted | Breach - formally accepted | Worsened | v1.0 | v1.0 | Assessed (evidence-supported) | Assessed (evidence-supported) | Like-for-like
R-003 | Sensitive data pasted into AI tools |  | 9 |  |  | Appetite breach |  | Breach - formally accepted | New in current |  | v1.0 |  | Assessed (evidence-supported) | Not comparable (composition)
R-004 | Missed regulatory deadlines | 12 | 8 | -4 | Tolerance breach | Appetite breach | Breach - not accepted | Breach - not accepted | Improved | v1.0 | v1.0 | Assessed (evidence-supported) | Assessed (evidence-supported) | Like-for-like
R-005 | Key-person dependency | 9 | 9 | 0 | Within appetite | Within appetite | Within appetite | Within appetite | Unchanged | v1.0 | v1.0 | Assessed (evidence-supported) | Assessed (evidence-supported) | Like-for-like
R-006 | Legacy ERP out of support | 15 | 15 | 0 | Appetite breach | Appetite breach | Accepted - expiry not set | Accepted - expiry not set | Unchanged | v1.0 | v1.0 | Assessed (evidence-supported) | Assessed (evidence-supported) | Like-for-like
R-007 | Supplier price inflation | 6 | 9 | 3 | Within appetite | Within appetite | Within appetite | Within appetite | Worsened | v1.0 | v1.0 | Assessed (evidence-supported) | Inherent only (no valid assessment) | Assessment basis changed
R-008 | Loss of anchor customer | 10 | 10 | 0 | Within appetite | Within appetite | Within appetite | Within appetite | Unchanged | v1.0 | v1.0 | Inherent only (no valid assessment) | Inherent only (no valid assessment) | Like-for-like

## Change Log
Change Log (voluntary record, NOT an audit trail)
Rows 6-8 are SAMPLE entries.
VOLUNTARY LOG: manually maintained and not tamper-resistant. Anyone with edit access can add, alter or delete entries, so completeness cannot be proven. For assurance use file version history, access controls, protected sheets and signed approvals held outside this workbook.
Date | Area | Item ID | Field changed | Previous value | New value | Reason / decision | Changed by | Approved by | Related snapshot date | Evidence / reference (ticket, minute, email)
2026-09-30 | Risk Register | R-004 | Control effectiveness (indicative) | Weak | Strong | Compliance calendar automation approved and tested | Head of Compliance | CISO | 2026-09-30 | EV-004 / ticket GRC-112
2026-09-30 | Risk Acceptance Register | AC-002 | Decision | Pending | Approved | Risk Committee approved with DLP condition | DPO | Risk Committee | 2026-09-30 | Committee minute 2026-09-30
2026-07-01 | Appetite | Cyber & Information Security | Tolerance limit | 12 | 10 | Board tightened appetite after annual review | Head of Risk | Board | 2026-08-31 | Board paper 2026-06

## Exception Register
Exception Register
Only a current, independently authorised, numeric-dated exception with exact Acceptance ID (Risk ID), the authority check name and issue count 1 can offset that authority check. It cannot offset other defects or make a risk acceptance eligible. Rows 6-7 are SAMPLE; EX-002 is intentionally unsupported and must be removed before operational use.
Exception ID | Check name | Scope (IDs or rows covered) | Issues covered | Rationale | Owner | Authorised by (not the owner) | Authorisation date | Expiry date | Exception status | Issues offset
EX-001 | Acceptances approved with insufficient authority | AC-001 (R-002) | 1 | SAMPLE: deliberate test row that demonstrates the authority check | Toolkit author | Toolkit reviewer | 2026-10-20 | 2026-12-31 | Valid | 1
EX-002 | Risks without a valid evidence-supported residual assessment | R-007 (expired), R-008 (none) | 2 | SAMPLE: deliberate test rows that demonstrate the inherent-basis fallback | Toolkit author | Toolkit reviewer | 2026-10-20 | 2026-12-31 | Invalid issue count - not counted | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Checks
Data Integrity Checks & Release Gate
Issue counts identify failed checks, not unique root causes. Only exact scoped authority exceptions can offset a check; they do not make an acceptance eligible. Rows 25-28 are diagnostics already covered above.
Sample data present? (Yes/No) | Yes
Check | Issues found | Authorised exceptions (Exception Register) | Unresolved defects | Status
Duplicate Risk IDs | 0 | 0 | 0 | OK
Risks with a category not listed on Appetite | 0 | 0 | 0 | OK
Risks with missing or invalid inherent ratings | 0 | 0 | 0 | OK
Treatment actions linked to an unknown Risk ID | 0 | 0 | 0 | OK
Appetite rows failing validity (tolerance, approval, effective date, version, review) | 0 | 0 | 0 | OK
Accepted risks with no approver named | 0 | 0 | 0 | OK
Acceptances approved with insufficient authority | 1 | 1 | 0 | Known sample exception
Acceptance rows linked to an unknown Risk ID | 0 | 0 | 0 | OK
KRIs linked to an unknown Risk ID | 0 | 0 | 0 | OK
Risk-control mappings to an unknown Risk ID | 0 | 0 | 0 | OK
Scenarios with missing or inconsistent loss estimates | 0 | 0 | 0 | OK
Aggregation links with unknown risk/driver or duplicate pair | 0 | 0 | 0 | OK
Scenarios without documented basis or confidence | 0 | 0 | 0 | OK
Change log entries missing reason or approver | 0 | 0 | 0 | OK
Risks without a valid evidence-supported residual assessment | 2 | 0 | 2 | DEFECT
Snapshot history duplicate rows (same date and risk) | 0 | 0 | 0 | OK
Snapshots with missing or mismatched control totals | 0 | 0 | 0 | OK
0
Total | 3 | 1 | 2
Release status | DEMONSTRATION: fictional data - 2 sample data-quality issue(s) | 0
Assessment approval/date failures (populated risks) | 2 | 0
Risks with unusable appetite configurations | 0 | 0
Exception records without exact permitted scope | 0
Risk register rows with no approved assessment | 0

## v4.1 Validation Guide
ERM v4.1 ¦ Governance and QA Release Notes
Control area | New operational rule
Appetite governance | Only currently effective, approved threshold configurations permit authoritative breach statuses.
Review overdue | Previously approved and effective limits remain applied, but review overdue is flagged in Appetite.
Bad threshold | Missing, future, invalid and duplicate threshold configurations return Configuration status, not false pass/fail.
Residual assessment | Requires numeric integral 1-5 scores, evidence, assessor, approval owner, valid date and explicit Approved decision.
Future dates | Future or missing assessment dates invalidate the residual assessment; inherent scores provide conservative fallback.
Exception offset | Insufficient-authority exception must match exact Acceptance ID and Risk ID, check name and current authorisation.
Exceptions elsewhere | No general issue-count offsets permitted; fix underlying defect rather than hiding it.
Historical snapshot | Manual value-only capture is not immutable; preserve records externally with document controls.
Quantitative analysis | Scenario estimates are illustrative and must not be treated as precise financial forecasts.
Status | Requires recalculation and interaction testing in Microsoft Excel before external operational use.
ID | Test scenario | Expected behaviour | Test type
T01 | Set Appetite F8 blank | Risk U category becomes Configuration: Not approved | Excel manual
T02 | Set Appetite K8 to future date | Risk U category becomes Configuration: Not yet effective | Excel manual
T03 | Set Appetite H8 to past | Risk U still classifies; Appetite I = Review overdue - approved | Excel manual
T04 | Reverse Appetite C8 and D8 | Risk U = Configuration: Invalid thresholds | Excel manual
T05 | Clear Risk Register AL6 | AI6 = Approval not confirmed and inherent score used | Excel manual
T06 | Enter future date in Risk Register AG6 | AI6 = Invalid assessment date; inherent score used | Excel manual
T07 | Enter residual likelihood 7 in K6 | AI6 = Invalid residual ratings | Excel manual
T08 | Edit Exception Register C6 to different acceptance ID | Checks C11 = 0; authority defect unresolved | Excel manual
T09 | Expire exception record I6 | Checks C11 = 0; authority defect unresolved | Excel manual
T10 | Sort Risk Register records | Risk and treatment IDs continue to associate correctly | Excel manual